## Inputs
Predecessors Relationships
ACTIVITIES | Description | Immediate Predecessors | Optimistic Time (a) | Most Likely Time (m) | Pessimistic Time (b) | Expected Value (a + 4m + b)/6 | Variance [(b-a)/6]2 | A | B | C | D | E | F
A | Plan Topic |  | 1 | 3 | 5 | 3 | 0.44444
B | Obtain Speakers |  | 2 | 4 | 6 | 4 | 0.44444
C | List Meeting Locations | B | 3 | 6 | 9 | 6 | 1 |  | 1
D | Select Location | A, C | 1 | 5 | 9 | 5 | 1.7778 | 1 |  | 1
E | Finalize Speakers Schedule | A | 1 | 2 | 3 | 2 | 0.11111 | 1
F | Prepare and mail Seminar Brochures | D, E | 2 | 8 | 20 | 9 | 9 |  |  |  | 1 | 1

## EST-EFT
Maximum of All EFTs
24 |  |  | A | B | C | D | E | F
| EST | EFT
A | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
B | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
C | 4 | 10 | 0 | 4 | 0 | 0 | 0 | 0
D | 10 | 15 | 3 | 0 | 10 | 0 | 0 | 0
E | 3 | 5 | 3 | 0 | 0 | 0 | 0 | 0
F | 15 | 24 | 0 | 0 | 0 | 15 | 5 | 0

## LST-LFT
Minimum Expected Project Completion Time
24 |  | A | B | C | D | E | F
| LST | 7 | 0 | 4 | 10 | 13 | 15
| LFT | 10 | 4 | 10 | 15 | 15 | 24
A |  | 24 | 24 | 24 | 24 | 24 | 24
B |  | 24 | 24 | 24 | 24 | 24 | 24
C |  | 24 | 4 | 24 | 24 | 24 | 24
D |  | 10 | 24 | 10 | 24 | 24 | 24
E |  | 13 | 24 | 24 | 24 | 24 | 24
F |  | 24 | 24 | 24 | 15 | 15 | 24

## PERT-CPM Table
| Min/Avg Project Completion Time |  |  | = | 24 |  | Target Time | 23 |  | Time | 30.5753
| Project Variance |  |  | = | 12.2222 |  | Probability | 38.74% |  | Target Probability | 97%
Activity | Description | AverageTime | EST | EFT | LST | LFT | Total Slack | Critical | Critical Activity Variance
A | Plan Topic | 3 | 0 | 3 | 7 | 10 | 7 | NO
B | Obtain Speakers | 4 | 0 | 4 | 0 | 4 | 0 | YES | 0.44444
C | List Meeting Locations | 6 | 4 | 10 | 4 | 10 | 0 | YES | 1
D | Select Location | 5 | 10 | 15 | 10 | 15 | 0 | YES | 1.7778
E | Finalize Speakers Schedule | 2 | 3 | 5 | 13 | 15 | 10 | NO
F | Prepare and mail Seminar Brochures | 9 | 15 | 24 | 15 | 24 | 0 | YES | 9

## Range Names
The inputs ranges are named to accommodate a total of 200 activities without renaming the ranges.
Explanantion | Name | Ranges
Optimistic Estimate | a | =Inputs!$D$3:$D$202
Pessimistic Estimate | b | =Inputs!$F$3:$F$202
Critical Activity Variance | cavariance | ='PERT-CPM Table'!$J$5:$J$204
Earliest Finish Times for All Activities | EFT_Range | ='PERT-CPM Table'!$E$5:$E$204
Earliest Start Time and Earlest Finish Time Table | EST_EFTtable | ='EST-EFT'!$A$4:$C$203
Input data for the problem | Inputs | =Inputs!$A$3:$H203
Latest Start and Latest Finish Time Table | LFT_Range | ='LST-LFT'!$C$4:$GT$4
Latest Finish Time for All Activities | LST_LFTtable | ='LST-LFT'!$C$2:$GT$4
Most Likely Time estimate for the activity | m | =Inputs!$E$3:$E$202
Maximum of All EFTs | MAXofAllEFTs | ='EST-EFT'!$A$2